## Process Plan
Task | Subject |  | Deliverable |  | Assign To | Progress | Start Date | Deadline
Analyze requirement | PWD Encryptor | CTCEPL-82 | CR & Use Case |  | Sean Li | 100% | 2017-06-26 | 2017-06-26
| PDF Generator | CTCEPL-83
Design | Program Structure |  | UI Design | PDF Generator | Jam Zhang | 100% | 2017-06-26 | 2017-06-30
|  |  |  | PWD Encryptor | Kate Li | 100% | 2017-06-26 | 2017-06-30
|  |  | Component Diagram |  | Sean Li | 100% | 2017-06-27 | 2017-06-28
|  |  | Class Diagram |  |  | 100%
|  |  | Activities Diagram |  |  | 100%
|  |  | Sequence Diagram |  |  | 100%
|  |  | Deployment Diagram |  |  | 100%
Develop | application | Application.java | Source Code |  | Sean Li | 100% | 2017-06-28 | 2017-07-03
|  | MainFrame.java |  |  |  | 100%
|  | AbstractView.java |  |  |  | 100%
|  | Console.java |  |  |  | 100%
| util | PropertiesLoader.java |  |  |  | 100%
|  | Properties.java |  |  |  | 100%
|  | Key.java |  |  |  | 100%
|  | ConnectionFactory.java |  |  |  | 100%
|  | RSAEncryptor.java |  |  |  | 100%
|  | FtpTransfer.java |  |  |  | 100%
|  | PdfGenerator.java |  |  |  | 100%
| PDF Generator | PdfGeneratorView.java |  |  | Jame Zhang |  | 2017-06-28 | 2017-07-03
PdfGeneratorController.java
PdfEventHandler.java
BusinessPartnerDao.java
BusinessPartnerDaoImpl.java
BusinessPartner.java
DBConfig.java
Parameter.java
| PWD Generator | PwdEncryptorView.java |  |  | Kate Li
PwdEncryptorController.java
PwdEventHandler.java
FtpConfig.java
PwdHolder.java
| Deploy Tool |  | Source Code |  | Kyanite Liu | 100% | 2017-06-28 | 2017-07-03
Test | Dev Test | PWD Encryptor |  |  | Kate Li |  | 2017-07-04 | 2017-07-04
|  | PDF Generator |  |  | Jame Zhang
|  | Deploy Tool |  |  | Kyanite Liu
| SIT Test | PWD Encryptor |  |  | Jam Zhang |  | 2017-07-05 | 2017-07-07
|  | PDF Generator |  |  | Kyanite Liu
|  | Deploy Tool |  |  | Kate Li
| UAT Test | PWD Encryptor |  |  |  |  | 2017-07-10 | 2017-07-14
PDF Generator
Deploy Tool
Source Code Review |  |  |  |  | Sean Li |  | 2017-07-04 | 2017-07-14
Release | [6 empty] | 2017-07-22 | 2017-07-22